## IT strategy execution plan
Tasks | Status
Phase 1 (Sept- 2020)
Create strategy plan | In Progress
Stakeholder buy in for plan | Pending
Introduce plan | Pending
Set up CLT (CTO Leadership Team)
Engineering Team | Started
Architecture Team | Started
Process Implementation Team | Started
Operational Team | Pending
Compliance Team | Pending
Reduce skill gap
Create skill gap matrix | In progress
Partner with essential skilled personal
Mobile development | In Progress
Data Science | In Progress
PHP | Pending
Python | Pending
Azure | Pending
ReactJS | Pending
Develop skill set internally
Mobile development | In Progress
Data Science | In Progress
PHP | In Progress
Python | In Progress
Azure | In Progress
ReactJS | In Progress
Finalize Governance structure | In Progress
Start TDD practices | Pending
Finalize KPI | Pending
Phase 2 (Dec 2020)
Implement Core Platform for internal development - | Pending
Logging | Pending
Monitoring | Pending
Routing | Pending
Scaling and provisioning | Pending
Data flow | Pending
Implement Core Platform for Pre developed product acquisition - | Pending
Implement partner engagement platform | Pending
Start BDD practices | Pending
Enable cloud based development environment | Pending
Start complience practices | Pending
Phase 3 (June 2021)
Start vendor agnotism | Pending